Master's Research Paper Time Frame Completion 
DEVELOPMENT STUDIES 
York University
Stage 1: Research Proposal
September to March year one
	Time Frame
	Student
	Supervisor
	Second Reader
	Grad Program

	1st week October
	Selecting a tentative topic for the MRT/MRP & making an effort to form a Supervisory committee
	
	
	

	1st week
November
	Submit a one page statement of research with research questions, objectives and hypothesis
	
	
	Grad Director approves outline

	Mid-November
	Finalize supervision
	Supervisor approves outline
	
	

	1st week
December
	MRT/MRP research proposal: Start writing
	
	
	

	January - March
	Put together the Research Proposal
	Supervisor approves the proposal. Finalize
the committee
members
	
	Grad Director approves the proposal and the committee members


Stage 2: Data collection
May-August, year one

Stage 3: Analysis, Writing and Submission of MRP/MRT
September - April year two
	Time Frame
	Student
	Supervisor
	Second Reader
	Grad Program

	September -
December
	Critical Reflection course. Writing on individual chapters in consultation with supervisor
	
	Second reader must be consulted
	

	2nd Week
January year two
	Submission of first full draft to the office. Office will submit draft to supervisor
	Review and provide comments in a timely fashion.
	
	

	February – Mid March year two
	Final Draft & Final Revision
	Supervisor approves outline
	
	

	Mid March to
April 15
	Oral Exam
	A written evaluation
will be submitted to the program office, signed by both the supervisor and the
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